CiteGuard

Final Year Project — Development Roadmap

13-week plan · Weeks 1-13 · Prepared for: Hamza, BS Software Engineering, 4th Year — Bahria University Islamabad

# 1. Timeline overview

This roadmap compresses the CiteGuard pipeline (parse → verify → semantic check → dashboard → report) into a 13-week (~3 month) build, aligned with the two-semester feasibility noted in the evaluation document. It now also accounts for three distinct actor roles — student, teacher, and researcher — who share the same verification pipeline but differ in permissions and dashboard views. Weeks 1-5 form Semester milestone 1 (proposal + design, including the role model); weeks 6-13 form milestone 2 (full feature set + demo-ready product).

| Timeframe | Phase | Focus |
| --- | --- | --- |
| Weeks 1-2 | Requirements & Planning | Finalize scope, lock SRS (incl. student/teacher/researcher roles), set up repo/environment, confirm API access |
| Week 3 | Auth & Role Architecture | Define permission matrix, role-aware DB schema, authentication and route guards |
| Weeks 4-5 | System Design | Use case & ERD diagrams per role, system architecture, UI wireframes/prototypes |
| Weeks 6-8 | Core Development | Document parsing, citation extraction, CrossRef/OpenAlex/Semantic Scholar integration |
| Weeks 9-10 | Semantic Layer & Dashboards | Sentence-BERT claim-checking, role-based dashboards, scoring logic |
| Week 11 | Enhancements & Testing | Retraction checking, open-access tags, permission-boundary testing, bug fixes |
| Weeks 12-13 | Reporting & Demo Prep | PDF/HTML report generation, documentation, viva/demo rehearsal |

# 2. Week-by-week breakdown

## Weeks 1-2 — Requirements & planning

Goal: a locked scope and a working dev environment.

- Finalize the SRS: confirm feature list (verification, semantic check, dashboard, report) and defer auto-repair + MCP endpoint to stretch goals

- Define the three actor roles — student, teacher, researcher — and write one user story per role so scope differences are explicit before design starts

- Register/test CrossRef, OpenAlex, and Semantic Scholar API access (all free, no key needed) — write small test scripts confirming each returns data

- Check Bahria University's HEC Digital Library access for optional IEEE Xplore coverage

- Set up repo structure: React frontend, FastAPI/Django backend, PostgreSQL, Docker

- Deliverable: approved proposal + confirmed API connectivity

## Week 3 — Auth & role architecture

Goal: the permission model is decided before any UI or pipeline code depends on it.

- Write a permission matrix: which actions each role can take (upload, view own results, view a class's results, batch-check, export audit trail, set policy)

- Extend the database design with role-aware tables: users (with a role field), classes/cohorts linking students to teachers, and a policy table for teacher-set citation rules

- Implement authentication (JWT or session-based) and role-based route guards on the FastAPI/Django backend

- Decide how a teacher-student link is established (invite code, class enrollment, admin import) — this affects both the DB schema and the onboarding flow

- Deliverable: permission matrix + working auth with role-gated API routes

## Weeks 4-5 — System design

Goal: every screen and data flow is on paper before code is written.

- Draw the use case diagrams: the shared verification workflow, plus the role-specific extensions for each actor (this document includes first drafts — see below)

- Design the ERD: users/roles, classes, uploaded papers, extracted citations, verification results, reports

- Design system architecture: upload service → parser → verifier → semantic checker → dashboard → report generator, with role checks at the API gateway layer

- Build low-fidelity prototypes/wireframes for: landing/upload page, results dashboard, report view (see prototypes below), plus rough sketches for the teacher class-overview and researcher batch views

- Deliverable: design document + clickable/visual prototypes

## Weeks 6-8 — Core development

Goal: a paper goes in, verified citations come out.

- Document parsing: extract in-text citations and the reference list using PyMuPDF or GROBID

- Build the verification pipeline: match each reference against CrossRef → OpenAlex → Semantic Scholar (in that priority order)

- Persist results to PostgreSQL (paper, citation, match status, source database), scoped to the uploading user's role and class

- Basic FastAPI/Django endpoints: upload, get status, get results — all behind the role-based route guards built in week 3

- Deliverable: working backend pipeline, testable via API calls, for a sample paper

## Weeks 9-10 — Semantic layer & role-based dashboards

Goal: the AI layer comes online, and each role sees the view that matches its use case.

- Integrate Sentence-BERT locally to compare claimed statement vs. cited abstract, produce a similarity/mismatch score

- Build the shared React dashboard shell: overall integrity score, per-citation status list, flags for mismatches

- Add the student view (own submissions only), the teacher view (class overview across students, policy settings), and the researcher view (batch upload, audit export)

- Wire dashboards to backend endpoints, gated by the auth/role logic from week 3

- Deliverable: end-to-end demo — upload a real paper, see a live scored dashboard that matches the logged-in role

## Week 11 — Enhancements & testing

Goal: the two 'low effort' enhancements are in, and the system (including role boundaries) is stress-tested.

- Add retraction checking using Crossref's retraction data

- Add open-access classification via Unpaywall (Gold/Green/Hybrid/Bronze)

- Test with multiple real papers of different lengths/reference counts; fix parsing edge cases

- Test permission boundaries specifically: confirm a student can't see another student's results, and a teacher can't see outside their own class

- Deliverable: feature-complete backend + regression-tested pipeline

## Weeks 12-13 — Reporting & demo prep

Goal: a polished, presentable product.

- Build downloadable PDF/HTML report generation (WeasyPrint)

- Polish dashboard UI, fix rough edges, add loading/error states

- Write final documentation: architecture notes, API list, known limitations

- Prepare the viva narrative around the honest-positioning angle: local-first deployment, non-technical researcher dashboard, multi-style support

- Rehearse the live demo end-to-end at least twice

- Deliverable: demo-ready CiteGuard + final documentation

# 3. Notes carried over from the evaluation

- Auto-repair suggestions and the API/MCP endpoint are Semester-2-style stretch goals — not required for this 12-week core build

- Keep the originality framing specific in every write-up: local-first processing, non-technical dashboard, and the retraction + open-access combo — not a broad “nobody does this” claim

- A 16GB RAM laptop with no dedicated GPU is sufficient; Sentence-BERT runs fine on CPU at this scale